## Sheet1
Product Backlog
User Story	Planned Sprint	Hours	Assignation
As a new user I want to be able to register so that I can save my information for future use	1	8	Hassan
As a user I want to be able to View all restaurants so that I can see variety of options when I want to order	1	8	Mohamed
As a user I want to be able to search restaurants so that I can get directly what I want if I have something in mind	1	10	Mohamed
As a user I want to see the menu of each restaurant so that I can order what I like	2	12	Aya
As a user I want to be able to add items to my cart so that I can confirm order at later time when I’m ready	2	8	Sara
As a user I want to be able to purchase the items in my cart and pay for it Online	2	15	Mohamed
As a restaurant I want to view all the orders I get so that I can make them and deliver to customers	2	13	Hassan
As a restaurant I want to change status of order so that the customer can view status of his order.	2	8	Aya